## Slide 1: Utilization Enhancement in Material Creation Service

## Slide 2
Project Title: Utilization Enhancement in Material Creation Service
Portfolio | MFG2
Project type | GB
Client | Signify EIM
Process | Product Master data
LOB | Data Management
Location | Chennai
Vertical | MFG
Project Category | Six Sigma
PACE Track PIN | 11829
Project Kick off date | 15-07-2019
Project Leader & Emp # | Ramamurthy.K(988529)
Project Expected Closure Date | 25-11-2019
Project Charter
Business Case : Material creation and maintenance is one of the main sub activities of Product Master Data. Team create and change the master data in SAP as per the request. This is new transition project and team receives both Mass and manual tickets in workflow tool. Currently team consists of 5 FTE, as part of contract requirement, team has to validate actual FTE required. Also, Infosys agreed 16% saving in FY20 at the time of contract Sign off ,This project critical to measure the utilization and enhance the efficiency in the process.
Problem Statement :Average working hours (Apr’19 to June’19) in PMD is 735 per month which has to be downsized as per client requirement.
In Scope: PMD 10NC\12NC Creation & Change Execution (EMEA,NAM,LATAM & CANADA)
Out of Scope: PMD Table maintenance & Product pricing
 | Metric | Unit of Measure | Baseline | Target
Y1 | Hours | Number | 735 | 514
* As applicable
Project Metric
Team Member 1 | 853241 | Babu Vijayaraghavan
Team Member 2 | 855437 | Lakshmipriya C
Team Member 3 | 855436 | Saravana Balaji K
Team Member 4 | 853706 | Mahendran Anandraj
Project Champion |  | Srinivasan D
PI Consultant | 838389 | Satheesh Jagannathan
Project Team
Developer , if any | Emp# | Name
Department of the Developer: |  | 
Goal Statement : Reduce the average working hours from 735 to 514 by October’19
Expected benefit $/FTE: 1.5 FTE

## Slide 3: AS IS Process Steps / Process Flow
Market Approver Validation if needed
Request Submission in Service now
Execution
Infosys Validation
STEP 1
STEP 2
STEP 3
STEP 4
STEP 5
Post validation
Attaching the template in Service now with comments
Closing the ticket in SNOW
Quality Check
STEP 6
STEP 7
STEP 8
Material Creation & Change Execution
If details are CORRECT, process and make it available in SAP
Request Submission in Service now
Performing Qquality check
If details are not sufficient, then request for additional details
STEP 1
STEP 2
STEP 3
STEP 4
2. Offset
Validating Input
Request Submission in Service now
Contacting Requestor for clarification\additional information
Checking Duplicate
Contacting Market Approver for the Rejecting confirmation
STEP 1
STEP 2
STEP 3
STEP 4
STEP 5
Updating the same comments in snow while closing
STEP 6
3. Queries

## Slide 4
Supplier | Input | Process | Output | Customer
Requestor | Ticket Service now Supporting documents | Validation Obtain approval from stakeholders Creation/Change in SAP Ticket closure | Ticket closure Create\Update Master Data | Requestor
SIPOC

## Slide 5: CTQ Tree
PMD
Reducing Manual intervention
Query Handling
Improve Utilization %
Reduce execution time%
Contacting requestors to follow standard templates
Elimination of non - value added activities

## Slide 6: Measure

## Slide 7
Performance Measure | Data Source & location | Sample Size | Who will collect data | When will data be collected | Data period
Utilization hours | Service now | 100% | Ramamurthy.K | Monthly Once | Apr’19 ,May’19 & June ‘19
Measurement Plan
Project G | : Reduce the average working hours from 735 to 514 by October’19

## Slide 8
Current Volume trend ( April, May & June ‘19 )
Average ticket processed per day 17 and average transaction processed per day 15695
Chart: Volume Trend
| Apr'19 | May'19 | Jun'19
Volume | 443 | 490 | 336
Average | 17.72 | 17.5 | 15.27
Chart: Transaction Trend
| Apr'19 | May'19 | Jun'19
Transactions | 251338 | 555999 | 368612
Average | 10472.4 | 19857.1 | 16755.09

## Slide 9
Data Analysis – More effort spend Area
1
2
Time taken foe system upload consumes more time
Average Post validation time consumes more time
Inferences
Chart: 
| Manual work - Post validation | Manual work - Pre Validation | Manual work - Recording/searching macro | Manual work - Ticket validation | Uplaod in System
Average Time Taken | 6.45 | 3.85 | 7 | 1.9167 | 9.9667

## Slide 10
Utilization Measurement
Activities | Before Improvement
Average number of tickets processed manually day | 17
AHT for manual processing - mins | 14.27
Total Manual work - Mins | 242.59
Total Manual work - hours per day | 4.04
Average transaction processed per day | 15695
Average time spend in upload in system per day (hours) | 16
Waiting time between upload | 9.65
Clarification/Email handling time per day | 5
Time required per day | 34.69
Time required per month | 763.25

## Slide 11: Analyze

## Slide 12
Cause and Effect Analysis
Machine
Man
Measurement
Material
Method
Input provided in the request not clear
No proper template format in SNOW
No Proper backup created
80% of the request is mass loads
Knowledge gap, process dependency
SLA miss due to High number of transactions
VDI issue
Limitation of SAP job roles
Lack of Winshuttle License to upload the requests
Unable to perform quality check for the Transaction performed

## Slide 13
Data Analysis
Data Analysis – Mass load Vs Transaction volume
Average transaction processed per day is 31000
Transaction volume is indirection proportion with ticket volume

## Slide 14
Data Analysis –Day to Day Trend
Chart: Material transaction Volume on daily basis
 | 26874 | 36296 | 4290 | 5044 | 30033 | 0 | 34845 | 5553 | 51 | 9196 | 8017 | 33234 | 851 | 14645 | 1238 | 5271 | 2934 | 289 | 4538 | 7693 | 3010 | 11164 | 2802 | 3470
Average transaction varies from 5000 to 15000 for most of the time. Q3 Transaction volume is 37000

## Slide 15: Improve

## Slide 16
Solution Deployed
S.Nos | Type | Cause | Solution Deployed | Quantifiable / Non Quantifiable | date of deployment | Status | Responsible
1 | Template standardization | Requestor not following the correct template in Service now | 1. Template standardization has been completed | Quantifiable(utilization%) | 15-Apr-19 | Completed | Babu
 |  |  | 2. KT has been provided to requestors to follow the templates |  |  |  | 
2 | Quality Check | Manual Quality check for material creation is a repetitive process | Reduce the time by using SE16N report for Post validations for all creation requests | Quantifiable(utilization%) | 3-Jul-19 | Completed | Babu\Lakshmi
3 | Lack of Winshuttle | Missed SLA for many tickets due to lack of Winshuttle ID | Additionally received licenses for executing the requests on time without missing the SLA | Quantifiable | 15-Aug-19 | Completed | Ram\Saravana
 |  |  | Runner License can be used simultaneously |  |  |  | 
4 | Cross training | Workload not balanced | Team members has been cross trained effectively to have knowledge on all the process and support in case of urgency | Quantifiable | 10-Jun-19 | Completed | Lakshmi, Mahendran, Babu
5 | SAP Access to all team members | Due to Job role limitation, it is difficult to assign tickets to team members to support if the volume is High | Requested for additional Job roles to the team members | Quantifiable | 04-Oct-19 | Completed | Ramamurthy.K
 |  |  | All the team members can get cross trained and process tickets |  |  |  | 

## Slide 17: Control

## Slide 18
S1
Activities | Before Improvement | After Improvement
Average number of tickets processed manually day | 17 | 17
AHT for manual processing - mins | 14.27 | 9.5
Total Manual work - Mins | 242.59 | 161.5
Total Manual work - hours per day | 4.04 | 2.69
Average transaction processed per day | 15695 | 15695
Average time spend in upload in system per day (hours) | 16 | 18
Waiting time between upload | 9.65 | 0
Clarification/Email handling time per day | 5 | 3.5
Time required per day | 34.69 | 24.19
Time required per month | 763.25 | 532.22

## Slide 19
S3
Allocating to specific person having license to upload the mass Requests
Input Validation
Quality Check
Request Execution based on License availability and SAP access roles
Request completion
STEP 1
STEP 2
STEP 3
STEP 4
STEP 5
Allocating the requests to team members to perform the ticket
Input Validation/Clarification
Quality Check
Executing the Mass requests
Request completion
STEP 1
STEP 2
STEP 3
STEP 4
STEP 5
Before
After
Note: Steps highlighted in green has been improved and sustained by getting additional license to perform the ticket without missing SLA, cross trained all the team members internally and utilized efficiently

## Slide 20
Project Metric: Utilization Enhancement in Material Creation Service UOM: hrs | Baseline | Target | Improvement
 | Average |  | 
Metric – Mean | 763 | 550 | 532
Supporting data on improvement and Financial Validation
Project Benefits
Excel Attachment
Benefits calculation
Soft Benefits – Qualitative: Utilization has been increased and 1.5 FTE reduced as outcome of the project
Improvement data (1 month data for mistake proofing solutions. 3 months data for general solutions )
Baseline performance data
Mail Attachment
Finance team sing off mail
On financial benefits, if applicable
Champion/ COH Sign off mail
on metric improvement & benefits,
Mail Attachment
Mail Attachment
Consultant / Lead Consultant
Sing off as applicable
Client Sign off (as applicable)
on metric improvement & benefits,
Appreciations / Awards
FTE Saved/Man hours saved * | Billing Rate * | Total Annualized Benefits in $ (C) | Type of Benefits | Benefit to
1.5 | Jl-2,7942, JL-3 4928 | 8899 | Hard | Infosys BPM
Actual Closure dates
Define : 10– Apr – 19
Measure: 14 May--19
Analyze : 19 – Jun - 19
Improve : 22-- Aug- 19
Control : 01- October - 19

## Slide 21
5. Dissemination Learnings
NA
3. How the process has been improved &Sustained?
Additional license has been deployed to upload the materials and arrested the SLA miss tickets
New Job roles has assigned to all team members, so that processors can be used effectively in all the sub services in Product domain
Can able to Mange the priority volumes due to additional runner license
Process dependency has been reduced by creating proper backup matrix
Infosys 1.5 FTEs hard benefit worth of productivity delivered
1.5 FTE saved accounting as 4928 USD per Annum
4. Value to client / Infosys BPO
Analysis of the data and Root Causes
Multiple kaizen was implemented by standardizing the templates in 10ns\12nc services
Persons idle time has been identified and eliminated by creating proper backup plan and cross trainings
1. Recognize Improvement Opportunities
Material creation and maintenance is one of the main sub activities of Product Master Data. Team create and change the master data in SAP as per the request. This is new transition project and team receives both Mass and manual tickets in workflow tool. Currently team consists of 5 FTE, as part of contract requirement, team has to validate actual FTE required. Also, Infosys agreed 16% saving in FY20 at the time of contract Sign off ,This project critical to measure the utilization and enhance the efficiency in the process.
1. We have 5 resources in 12nc service and the actual effort hours are 735 hours per month. This project is aimed to reduce the effort hours to 514 by October2019.
.
Project Leader | Ramamurthy.K
Project End Date | Oct ’19
Project type | GB
Client | Signify
Process | PMD
LOB | Data Management
Location | Chennai
Vertical | MFG
Category | Six sigma
2. What improvements
One Pager Case study
PPM Level | 
PPM Levers | 
PIN | 
LAPRO or any other IDs | 
Project Title: Utilization Enhancement in Material Creation Service